Approving the Timetable for the Review and Approval of the Revised Computer Technology Standards of Learning

Resolution Number 2012-12

April 26, 2012

The Board of Education approves the timetable for review of the Computer Technology Standards of Learning.

- The timetable is as follows:

PROPOSED SCHEDULE FOR REVIEW OF THE

COMPUTER TECHNOLOGY STANDARDS OF LEARNING

May 4, 2012	A Superintendent’s Memorandum will be distributed to announce the review process schedule, the availability of a Standards of Learning review/comment page on the Department of Education Web site, and request that division superintendents share information about the Web site with instructional staff.

The Department of Education will post on its Web site a Standards of Learning review/comment page for the 2005 Computer Technology Standards of Learning. The page will be active for 30 days.

May 15, 2012	The Department of Education will meet with the Virginia Educational Technology Advisory Committee (VETAC), an advisory committee that advises the Board of Education on educational technology matters through the Superintendent of Public Instruction. This committee will begin review of comments, various international standards, and the Essential Elements of ICT Literacy to make recommendations for potential changes.

June-July 2012	The first draft of the 2012 Computer Technology Standards of Learning will be prepared, reflecting recommendations from VETAC members as well as comments from the Web page.

The draft will be made available to technology directors, instructional technology resource teachers, librarians, Virginia’s teacher colleges, and various professional organizations for review and comment.

August 2012	The Department of Education and the VETAC Executive Committee will meet to review the feedback and prepare the draft 2012 Computer Technology Standards of Learning for first review by the Board of Education.

September 27, 2012	The Department of Education will present the proposed document to the Board of Education for first review.

October 2012	The proposed 2012 Computer Technology Standards of Learning document will be distributed for public comment. The document will be placed on the Virginia Department of Education Web site for review. Public hearings will be held as prescribed by the Board of Education.

November 29, 2012	The Superintendent of Public Instruction will make a recommendation to the Board of Education for final review and adoption of the proposed 2012 Computer Technology Standards of Learning. The final document will be posted on the Department of Education’s Web site and school divisions will be apprised of its availability.

David M. Foster
President
Minutes of April 26, 2012