Adopting a Work Plan for the Review of the Standards of Quality

Resolution Number 2012-19

May 24, 2012

The Board of Education approves the work plan for the review of the Standards of Quality.

The work plan to review the Standards of Quality includes:

SOQ Committee Meeting – April 25

- Review the provisions of the SOQ (§§ 22.1-253.13:1 through 22.1-253.13:9 of the Code of Virginia)

- Determine the questions that will guide the Board’s review of the SOQ

- Review the draft work plan

- Ask stakeholders for input on the guiding questions for the review and the draft work plan (April 27-May 17)

SOQ Committee Meeting – May 23

- Review stakeholder comments on the guiding questions for the review and finalize the guiding questions

- Review stakeholder comments on the work plan and finalize the work plan

Board of Education Meeting – May 24

- First review of the work plan

- Set the public comment period – May 24 through November 15

SOQ Committee Meeting – June 27

- Invite stakeholders to present recommendations to the Board

- Accept public comment

Board of Education Meeting – June 28

- Final review of the work plan

SOQ Committee Meeting – July 25

- Invite stakeholders to present recommendations to the Board

- Accept public comment

SOQ Committee Meeting – September 26

- Discuss draft recommendations to amend the SOQ

- Accept public comment

Board of Education Meeting – September 27

- First review of recommendations to amend the SOQ

Public Hearings – in October

- Northern Virginia

- Tidewater

- Central Virginia

- Southwest Virginia

Board of Education Meeting – November 29

- Final review and approval of recommendations to amend the SOQ

David M. Foster
President
Minutes of May 24, 2012